## Sheet1
March | Person Resp | Due Date | April | Person Resp | Due Date | May | Person Resp | Due Date | June | Person Resp | Due Date | July | Person Resp | Due Date | August | Person Resp | Due Date | September | Person Resp | Due Date | October | Person Resp | Due Date | November | Person Resp | Due Date | December | Person Resp | Due Date | January | Person Resp
Finalize Campaign Theme (includes Pastor Mike's campaign theme sheet) |  |  | Identify New Hosts |  |  | 1st draft script due |  |  | Start Curriculum Questions(with answers) |  |  | Online sign up via website |  |  | Music for videos |  |  | HOST book and member books completed/printed and bound | [5 empty] | Thank you event
Set design and planning |  |  | Pastors begin writing scripts |  |  | Draft and send questions for testimonials to answer |  |  | Final draft of scripts to Video Team |  |  | begin Edit videos/ commercial |  |  | Graphics for commercial/video |  |  | DVD completed with case and duplicates incl case design and CD label design | [5 empty] | Evaluation e-mailed
July 9th week
[9 empty] | Film Testimonies |  |  | Postcard – Life Groups are coming |  |  | Page in bulletin in Sanctuary?
Email blast
[9 empty] | Film Testimonies |  |  | Courtyard signs |  |  | Email blasts
Web
[9 empty] | Film Testimonies |  |  | Access
Letter?
|  |  | Identify and ask testimonials for video | [5 empty] | Film video - film testimonials and commercial too, depending on location |  |  | Film testimonies, and commercial |  |  | Curriculum and leader book completed to give to Designer |  |  | continuation of courtyard sign-ups, church cards, commercial, etc.
[9 empty] | Film Commercial, Campaign Videos, testimonies and experts |  |  | Curriculum completed to give to Chris | [5 empty] | continuation of courtyard sign-ups, church cards, commercial, etc. |  |  | e-blasts | Debi/Christina | each week in Sept up to campaign start
[9 empty] | Postcard, Website updated and Facebook/Twitter – Life Groups Campaign is coming | [5 empty] | courtyard/auditorium banner, slide in auditorium, access,bulletin inserts |  |  | e-blasts
[15 empty] | e-blasts |  |  | HOST training meetings
Bookmarks to hand out Sunday before School Starts
bulletin sign-up card insert w/Pastor appeal following commercial and courtyard sign ups
Commercial edited to start showing: Date-Date